## Executive Summary
FirstNet Website Migration Plan
Migration to AEM Edge Delivery Services
Total Pages: | 700+ (per sitemap)
Website: | www.firstnet.com
Project Type: | Public Safety Network Site Migration
Block Variations Documented: | 106
Content Types:
Devices, Rate Plans, Coverage, Industry Solutions, Community, Support, Apps
DISCLAIMER:
This block inventory was compiled through automated crawling and manual review of www.firstnet.com.
Block variations represent patterns observed at the time of analysis and may not capture all edge cases,
dynamic content states, or pages behind authentication. Actual implementation may require additional
blocks or variations not documented here. Screenshots are point-in-time captures and page content
may have changed since collection. This document is intended for planning purposes only.

## Site Structure
Category | URL Pattern | Description
Homepage | https://www.firstnet.com/ | Main entry point
Power of FirstNet | https://www.firstnet.com/power-of-firstnet.html | Mission and history
Coverage | https://www.firstnet.com/coverage.html | Network coverage and map
Rate Plans | https://www.firstnet.com/plans.html | Individual and agency plans
Devices | https://www.firstnet.com/devices.html | Phones, tablets, watches, accessories
Device Detail | https://www.firstnet.com/devices/phones/*.html | Individual product pages
Apps | https://www.firstnet.com/apps.html | Application ecosystem
Industry Solutions | https://www.firstnet.com/industry-solutions.html | Industry landing page
Industry Detail | https://www.firstnet.com/industry-solutions/*.html | Law enforcement, Fire, EMS, Healthcare
Community | https://www.firstnet.com/community.html | News, blogs, case studies
News | https://www.firstnet.com/community/news/*.html | News articles
Blogs | https://www.firstnet.com/community/blogs/*.html | Blog posts
Help | https://www.firstnet.com/help.html | Help center
FAQ | https://www.firstnet.com/faq.html | Frequently asked questions
Contact | https://www.firstnet.com/contact-us.html | Contact information
Sign Up | https://www.firstnet.com/sign-up.html | Registration flow
Eligibility | https://www.firstnet.com/eligibility-verification.html | Eligibility verification
Mission Critical | https://www.firstnet.com/mission-critical.html | Push-to-talk solutions
Offers | https://www.firstnet.com/offers/*.html | Current promotions
Why FirstNet | https://www.firstnet.com/why-firstnet.html | Benefits and comparison page
Phones by Brand | https://www.firstnet.com/devices/phones.html | Phones grouped by manufacturer
Accessories by Brand | https://www.firstnet.com/devices/accessories.html | Accessories grouped by brand
404 Error | https://www.firstnet.com/404 | Page not found

## Block Inventory
Block Type | Variation | Description | Page URL | Screenshot
Header Navigation | Global | Logo, hamburger menu, sign up, login | https://www.firstnet.com/ (all pages)
Footer | Global | Logo, sitemap, support links, social, legal | https://www.firstnet.com/ (all pages)
Email Subscription Form | Global | Blue background with email input + category dropdown | https://www.firstnet.com/ (all pages)
Quick Links Carousel | Homepage | 8 icon pill links horizontal carousel | https://www.firstnet.com/
Hero Section | Homepage | Mission-critical messaging with background image | https://www.firstnet.com/
Offer Cards Carousel | Homepage | 3 device/plan offer cards with images | https://www.firstnet.com/
Why FirstNet Section | Homepage | 3-column value props with heading | https://www.firstnet.com/
News Cards | Homepage | 3 article preview cards with images | https://www.firstnet.com/
Contact CTA Banner | Homepage | Dark background "Connect with specialist" | https://www.firstnet.com/
Page Hero | Plans | Breadcrumb + heading + description | https://www.firstnet.com/plans.html
Anchor Navigation | Plans | Horizontal jump links to sections | https://www.firstnet.com/plans.html
Individual Plan Section | Plans | Tabbed content with plan details | https://www.firstnet.com/plans.html
Rate Plan Features | Plans | 4-column features with icons | https://www.firstnet.com/plans.html
Promo Banner | Plans | $300 reward card offer banner | https://www.firstnet.com/plans.html
Agency Pricing Cards | Plans | Tabbed 3-column pricing cards | https://www.firstnet.com/plans.html
International Plans Cards | Plans | 3 international plan comparison cards | https://www.firstnet.com/plans.html
PDF Download Links | Plans | Arrow links to PDF documents | https://www.firstnet.com/plans.html
Legal Disclaimers | Plans | Expandable legal text section | https://www.firstnet.com/plans.html
Hero with CTA | Coverage | Purpose-built messaging with Get started CTA | https://www.firstnet.com/coverage.html
Interactive Map | Coverage | Embedded Leaflet coverage map with layers | https://www.firstnet.com/coverage.html
Coverage Benefits | Coverage | 3-column Band 14, 5G, Investment features | https://www.firstnet.com/coverage.html
Connectivity Ecosystem | Coverage | 3 image+text cards (In-building, In-field, In-vehicle) | https://www.firstnet.com/coverage.html
Satellite Innovation | Coverage | Text block about satellite connectivity | https://www.firstnet.com/coverage.html
Response Operations Group | Coverage | Blue background promo section | https://www.firstnet.com/coverage.html
Customer Stories Carousel | Coverage | 5 story cards with overlay text | https://www.firstnet.com/coverage.html
Get Started Cards | Coverage | 2-column Agencies vs Individuals cards | https://www.firstnet.com/coverage.html
Hero with Offer Banner | Devices | Expandable offer banner + hero | https://www.firstnet.com/devices.html
Compatibility Link | Devices | Arrow link to check device compatibility | https://www.firstnet.com/devices.html
Quick Links Inline | Devices | Horizontal text quick links | https://www.firstnet.com/devices.html
Catalog Overview | Devices | Heading + description text block | https://www.firstnet.com/devices.html
Product Cards Grid | Phones | 3 phone product cards with images | https://www.firstnet.com/devices.html
Product Cards Grid | Tablets | 3 tablet product cards with images | https://www.firstnet.com/devices.html
Product Cards Grid | Watches | 3 smartwatch product cards | https://www.firstnet.com/devices.html
Product Cards Grid | Connected Devices | 3 router/IoT device cards | https://www.firstnet.com/devices.html
Product Cards Grid | Accessories | 3 accessory product cards | https://www.firstnet.com/devices.html
Product Cards Grid | Enhancements | 3 coverage enhancement device cards | https://www.firstnet.com/devices.html
FAQ Accordion | Devices | Expandable device FAQ questions | https://www.firstnet.com/devices.html
Hero Simple | Community | Breadcrumb + heading + eligibility CTA | https://www.firstnet.com/community.html
Featured Case Study | Community | Full-width text block with read more | https://www.firstnet.com/community.html
Case Studies Carousel | Community | 12 overlay cards carousel | https://www.firstnet.com/community.html
Health Wellness Promo | Community | Blue background resource promo | https://www.firstnet.com/community.html
News Articles List | Community | Date + title + description list | https://www.firstnet.com/community.html
Blogs/Videos Tabs | Community | Tabbed content for blogs and videos | https://www.firstnet.com/community.html
Promo Banner Top | Industry | FirstNet and Family promotional banner | https://www.firstnet.com/industry-solutions.html
Industry Hero | Industry | Industries heading with description and eligibility CTA | https://www.firstnet.com/industry-solutions.html
Industry Category Cards | Industry | 8 industry category cards in 2 rows | https://www.firstnet.com/industry-solutions.html
Hero with Login | Help | Login to manage account CTA | https://www.firstnet.com/help.html
Popular Topics Grid | Help | 6 icon topic cards | https://www.firstnet.com/help.html
Eligibility Accordion | Help | Expandable eligibility help sections | https://www.firstnet.com/help.html
Refer-A-Friend Promo | Help | Reward card promotional block | https://www.firstnet.com/help.html
Device Help Accordion | Help | NumberSync, eSIM, FirstNet Ready tabs | https://www.firstnet.com/help.html
Product Guides Accordion | Help | Cell Booster, Deployables, MegaRange guides | https://www.firstnet.com/help.html
Help Links Cards | FAQ | 3 action cards (Login, Eligibility, Support) | https://www.firstnet.com/faq.html
Quick Links Tabbed | FAQ | Tabbed support articles with image | https://www.firstnet.com/faq.html
FAQ Accordion | Troubleshooting | Expandable troubleshooting FAQs | https://www.firstnet.com/faq.html
Migration CTA | FAQ | FirstNet and Family migration promo | https://www.firstnet.com/faq.html
FAQ Accordion | Plans/Offers | Expandable plan and offer FAQs | https://www.firstnet.com/faq.html
Products Cards Row | FAQ | 4 product category cards | https://www.firstnet.com/faq.html
Device Hero | Detail | Product image + feature bullet list | https://www.firstnet.com/devices/phones/iphone-17-pro.html
Shop Now CTA | Detail | Primary shop button | https://www.firstnet.com/devices/phones/iphone-17-pro.html
Legal Footnotes | Detail | Detailed product disclaimers | https://www.firstnet.com/devices/phones/iphone-17-pro.html
App Hero Carousel | Apps | 5-slide carousel with app features and CTAs | https://www.firstnet.com/apps.html
App Catalog Features | Apps | Image + text section about app library | https://www.firstnet.com/apps.html
App Uses Carousel | Apps | 6 overlay cards for app use cases | https://www.firstnet.com/apps.html
Featured Apps Carousel | Apps | 9 app cards with descriptions and CTAs | https://www.firstnet.com/apps.html
FirstNet Central Section | Apps | Image + text block about network control | https://www.firstnet.com/apps.html
Developer Program Section | Apps | Text + CTA for app developers | https://www.firstnet.com/apps.html
Download CTA Banner | Apps | Blue background with PDF download button | https://www.firstnet.com/apps.html
Contact Hero | Contact | Simple heading "Reach out to our experts" | https://www.firstnet.com/contact-us.html
Contact Cards Grid | Contact | 4 icon cards for contact options | https://www.firstnet.com/contact-us.html
Page Hero with CTA | Power | Full-width hero with eligibility CTA | https://www.firstnet.com/power-of-firstnet.html
History Text Section | Power | Long-form text about FirstNet origins | https://www.firstnet.com/power-of-firstnet.html
Contact Specialist CTA | Power | Blue button to contact specialist | https://www.firstnet.com/power-of-firstnet.html
Video Feature Block | Power | Image + text with Watch Now button | https://www.firstnet.com/power-of-firstnet.html
Story Cards Carousel | Power | 6 overlay cards with video/explore links | https://www.firstnet.com/power-of-firstnet.html
Error Page Content | 404 | "Page not found" messaging with tips | https://www.firstnet.com/404
Recommended Pages List | 404 | List of suggested page links | https://www.firstnet.com/404
Article Header | News | Title + subtitle headline block | https://www.firstnet.com/community/news/att-10-year-investment-transform-public-safety-broadband-network.html
Article Date | News | Publication date display | https://www.firstnet.com/community/news/att-10-year-investment-transform-public-safety-broadband-network.html
Article Hero Image | News | Full-width featured image | https://www.firstnet.com/community/news/att-10-year-investment-transform-public-safety-broadband-network.html
Article Body Content | News | Rich text with headings, lists, links | https://www.firstnet.com/community/news/att-10-year-investment-transform-public-safety-broadband-network.html
Industry Hero Carousel | Law Enforcement | 2-slide hero with messaging | https://www.firstnet.com/industry-solutions/law-enforcement.html
Anchor Navigation | Law Enforcement | Horizontal jump links for sections | https://www.firstnet.com/industry-solutions/law-enforcement.html
Why FirstNet Section | Law Enforcement | 2-column text block about benefits | https://www.firstnet.com/industry-solutions/law-enforcement.html
Appreciation Section | Law Enforcement | Thank you message with video CTA | https://www.firstnet.com/industry-solutions/law-enforcement.html
Customer Quote Block | Law Enforcement | Blue banner with quote and attribution | https://www.firstnet.com/industry-solutions/law-enforcement.html
Features Carousel | Law Enforcement | 3-card carousel (Modernized, Ready, Secure) | https://www.firstnet.com/industry-solutions/law-enforcement.html
Customer Stories Carousel | Law Enforcement | 9 video/PDF story cards | https://www.firstnet.com/industry-solutions/law-enforcement.html
Get Started Cards | Law Enforcement | 2-column Agencies vs Individuals cards | https://www.firstnet.com/industry-solutions/law-enforcement.html
Offer Hero | FirstNet & Family | Discount headline with plan pricing | https://www.firstnet.com/offers/firstnet-and-family.html
Benefits Grid | FirstNet & Family | 4 icon cards showing plan benefits | https://www.firstnet.com/offers/firstnet-and-family.html
Legal Disclaimers Expanded | FirstNet & Family | Full legal terms in text blocks | https://www.firstnet.com/offers/firstnet-and-family.html
Tabbed Plan Comparison | FirstNet & Family | FirstNet vs Family plan cards with tabs | https://www.firstnet.com/offers/firstnet-and-family.html
Device Offer Cards | FirstNet & Family | 3 product cards with pricing/CTAs | https://www.firstnet.com/offers/firstnet-and-family.html
FAQ Accordion | FirstNet & Family | Expandable offer FAQs | https://www.firstnet.com/offers/firstnet-and-family.html
Get Started Cards | FirstNet & Family | New vs Existing customer cards | https://www.firstnet.com/offers/firstnet-and-family.html
Sign Up Hero | Sign Up | Hero with eligibility messaging and CTA | https://www.firstnet.com/sign-up.html
Anchor Navigation | Sign Up | Horizontal jump links for sections | https://www.firstnet.com/sign-up.html
Eligibility Cards | Sign Up | 2-column Individual vs Agency signup cards | https://www.firstnet.com/sign-up.html
Featured Offer Card | Sign Up | Large offer card with image | https://www.firstnet.com/sign-up.html
Benefits Row | Sign Up | 3 value prop icons with descriptions | https://www.firstnet.com/sign-up.html
FAQ Accordion | Sign Up | Expandable sign-up related FAQs | https://www.firstnet.com/sign-up.html
Mission Critical Hero | Mission Critical | Hero with PTT solutions messaging | https://www.firstnet.com/mission-critical.html
Anchor Navigation | Mission Critical | Solutions, Resources, Get started links | https://www.firstnet.com/mission-critical.html
Solutions Product Cards | Mission Critical | 2 product cards (Fusion, Rapid Response) | https://www.firstnet.com/mission-critical.html
Case Study Feature | Mission Critical | Image + text case study highlight | https://www.firstnet.com/mission-critical.html
Secondary Case Study | Mission Critical | Text-only case study block | https://www.firstnet.com/mission-critical.html
Get Started Cards | Mission Critical | 2-column Agency signup cards | https://www.firstnet.com/mission-critical.html
Eligibility Hero | Eligibility | Hero with verify now CTA | https://www.firstnet.com/eligibility-verification.html
Anchor Navigation | Eligibility | Documents, Impacts, FAQ links | https://www.firstnet.com/eligibility-verification.html
Document Cards | Eligibility | 2 cards for verification scenarios | https://www.firstnet.com/eligibility-verification.html
Warning Note | Eligibility | Important notice text block | https://www.firstnet.com/eligibility-verification.html
Impacts Table | Eligibility | Complex table with eligibility impacts | https://www.firstnet.com/eligibility-verification.html
FAQ Accordion | Eligibility | Verification-related FAQs | https://www.firstnet.com/eligibility-verification.html
Need Help Section | Eligibility | Contact customer service CTA | https://www.firstnet.com/eligibility-verification.html
Hero with CTA | Why FirstNet | Full-width hero with eligibility verification CTA | https://www.firstnet.com/why-firstnet.html
Benefits Grid | Why FirstNet | 3-column benefits with icons and descriptions | https://www.firstnet.com/why-firstnet.html
Comparison Image | Why FirstNet | Static image comparing FirstNet vs competitors | https://www.firstnet.com/why-firstnet.html
Audience Cards | Why FirstNet | 3 persona cards (Individuals, Agencies, Essential Services) | https://www.firstnet.com/why-firstnet.html
FirstNet Promise | Why FirstNet | Image + text section with video CTA | https://www.firstnet.com/why-firstnet.html
Insights Carousel | Why FirstNet | First responder insights story cards carousel | https://www.firstnet.com/why-firstnet.html
Hero Offer Carousel | Phones | Rotating hero with device offers and pagination dots | https://www.firstnet.com/devices/phones.html
Product Cards by Brand | Apple | Product grid organized by Apple brand | https://www.firstnet.com/devices/phones.html
Product Cards by Brand | Samsung | Product grid organized by Samsung brand | https://www.firstnet.com/devices/phones.html
Product Cards by Brand | Accessories | Accessory product grid organized by brand (Klein, Nite Ize, Samsung, Sonim) | https://www.firstnet.com/devices/accessories.html

## Block Reuse Summary
Block Type | Page Count | Page URLs
Header Navigation | All | Global component on all pages
Footer | All | Global component on all pages
Email Subscription Form | All | Global component on all pages
Page Hero (Breadcrumb) | 10+ | /plans.html, /coverage.html, /devices.html, /community.html, /help.html, /faq.html, /industry-solutions.html
Anchor Navigation | 5+ | /plans.html, /coverage.html, /community.html, /faq.html
FAQ Accordion | 4+ | /devices.html, /help.html, /faq.html
Product Cards Grid | 6 | /devices.html (phones, tablets, watches, connected, accessories, enhancements)
Promo Banner | 3+ | /, /plans.html, /help.html
Contact CTA Banner | 3+ | /, /plans.html, /coverage.html
Get Started Cards | 2+ | /coverage.html, /community.html
Tabbed Content | 4+ | /plans.html, /community.html, /faq.html
Case Studies Carousel | 2 | /community.html, /coverage.html
News Cards | 2 | /, /community.html
Interactive Map | 1 | /coverage.html
Device Hero | 50+ | All device detail pages

## Page Distribution
Page Type | % of Total | Est. Count
Devices (Phones) | 25% | ~175
Devices (Tablets/Other) | 15% | ~105
Community/News | 20% | ~140
Help/Support | 15% | ~105
Industry Solutions | 10% | ~70
Apps | 8% | ~56
Core Pages | 7% | ~49
TOTAL | 100% | ~700

## Migration Phases
Phase | Focus Area | Deliverables | Dependencies | Complexity
Phase 1 | Foundation & Global Components | Header, Footer, Email Subscription, Global Styles, Design Tokens | None | Medium
Phase 2 | Core Page Templates | Homepage, Plans, Coverage - high traffic pages | Phase 1 | High
Phase 3 | Product Catalog | Devices listing, Device detail template, Product cards | Phase 1 | High
Phase 4 | Content Pages | Community, News articles, Blog posts, Case studies | Phase 1 | Medium
Phase 5 | Support Infrastructure | Help center, FAQ, Contact, 404 page | Phase 1 | Medium
Phase 6 | Industry Solutions | Industry landing, Industry detail pages (8 verticals) | Phase 2 | Medium
Phase 7 | Conversion Flows | Sign Up, Eligibility, Offers pages | Phase 2 | High
Phase 8 | Specialty Pages | Apps, Mission Critical, Power of FirstNet | Phase 1 | Medium
Phase 9 | Content Migration | Bulk import of 700+ pages using templates | Phases 1-8 | Low
Phase 10 | QA & Launch | Visual regression, Performance testing, SEO validation, Go-live | Phase 9 | Medium

## Effort Estimates
Component | Est. Days | Team Size | Notes
PHASE 1: FOUNDATION
Project Setup & Boilerplate | 2-3 | 1 Dev | AEM EDS repo, CI/CD, staging environment
Design Token Extraction | 3-5 | 1 Dev | Colors, typography, spacing from FirstNet brand
Global Header Block | 5-8 | 1 Dev | Responsive nav, hamburger menu, dropdowns
Global Footer Block | 3-5 | 1 Dev | Multi-column layout, social links
Email Subscription Block | 2-3 | 1 Dev | Form integration, validation
Phase 1 Subtotal | 15-24
PHASE 2: CORE PAGES
Hero Block (Multiple Variants) | 5-7 | 1 Dev | 6+ hero variations across site
Offer Cards Carousel | 4-6 | 1 Dev | Swiper/carousel, responsive cards
Anchor Navigation Block | 2-3 | 1 Dev | Sticky jump links, smooth scroll
Pricing/Plan Cards Block | 5-7 | 1 Dev | Tabbed interface, comparison layout
FAQ Accordion Block | 3-4 | 1 Dev | Expandable sections, multiple styles
CTA Banner Blocks | 2-3 | 1 Dev | Multiple color/layout variations
Homepage Template | 3-5 | 1 Dev | Page assembly and testing
Plans Page Template | 3-5 | 1 Dev | Complex layout with tabs
Coverage Page Template | 3-5 | 1 Dev | Map integration considerations
Phase 2 Subtotal | 30-45
PHASE 3: PRODUCT CATALOG
Product Card Grid Block | 4-6 | 1 Dev | 6 variations (phones, tablets, etc.)
Device Detail Hero | 3-5 | 1 Dev | Image gallery, feature list
Product Filters (if needed) | 5-8 | 1 Dev | Category filtering, search
Devices Listing Template | 2-3 | 1 Dev | Page with multiple grids
Device Detail Template | 2-3 | 1 Dev | Single product page
Phase 3 Subtotal | 16-25
PHASE 4: CONTENT PAGES
Case Study Carousel | 3-5 | 1 Dev | Overlay cards, video links
News/Article List Block | 2-3 | 1 Dev | Date, title, excerpt format
Article Body Block | 2-3 | 1 Dev | Rich text styling
Blogs/Videos Tabs Block | 3-4 | 1 Dev | Tabbed content interface
Community Template | 2-3 | 1 Dev | Page assembly
News Article Template | 2-3 | 1 Dev | Article page layout
Phase 4 Subtotal | 14-21
PHASE 5: SUPPORT
Popular Topics Grid | 2-3 | 1 Dev | Icon cards grid
Help Accordion Variants | 2-3 | 1 Dev | Multiple accordion styles
Contact Cards Grid | 2-3 | 1 Dev | 4-column icon cards
404 Error Page | 1-2 | 1 Dev | Simple error layout
Help Template | 2-3 | 1 Dev | Page assembly
FAQ Template | 2-3 | 1 Dev | Page assembly
Phase 5 Subtotal | 11-17
PHASE 6: INDUSTRY SOLUTIONS
Industry Category Cards | 3-4 | 1 Dev | 8-card grid layout
Industry Hero Carousel | 3-4 | 1 Dev | Multi-slide hero
Customer Quote Block | 2-3 | 1 Dev | Testimonial banner
Industry Landing Template | 2-3 | 1 Dev | Page assembly
Industry Detail Template | 2-3 | 1 Dev | Vertical-specific pages
Phase 6 Subtotal | 12-17
PHASE 7: CONVERSION FLOWS
Eligibility Cards Block | 3-4 | 1 Dev | CTA-focused cards
Benefits Row Block | 2-3 | 1 Dev | Icon + text value props
Impacts Table Block | 3-5 | 1 Dev | Complex data table
Sign Up Template | 2-3 | 1 Dev | Conversion-focused layout
Eligibility Template | 2-3 | 1 Dev | Page assembly
Offers Template | 2-3 | 1 Dev | Promotional layout
Phase 7 Subtotal | 14-21
PHASE 8: SPECIALTY
App Catalog Carousel | 3-5 | 1 Dev | App cards with CTAs
Solutions Product Cards | 2-3 | 1 Dev | 2-column feature cards
Video Feature Block | 2-3 | 1 Dev | Image + video CTA
Story Cards Carousel | 3-4 | 1 Dev | Overlay cards carousel
Apps Template | 2-3 | 1 Dev | Page assembly
Mission Critical Template | 2-3 | 1 Dev | Page assembly
Phase 8 Subtotal | 14-21
PHASE 9: CONTENT MIGRATION
Import Script Development | 5-8 | 1 Dev | Automated content extraction
Device Pages Bulk Import | 3-5 | 1 Dev | ~280 device pages
News/Blog Bulk Import | 2-4 | 1 Dev | ~140 articles
Help/Support Bulk Import | 2-3 | 1 Dev | ~105 pages
Remaining Pages Import | 3-5 | 1 Dev | ~175 misc pages
Phase 9 Subtotal | 15-25
PHASE 10: QA & LAUNCH
Visual Regression Testing | 5-8 | 1 QA | Cross-browser, responsive
Performance Optimization | 3-5 | 1 Dev | Core Web Vitals, LCP, CLS
SEO Validation | 2-3 | 1 Dev | Redirects, meta, structured data
Accessibility Audit | 3-5 | 1 Dev | WCAG compliance
UAT & Bug Fixes | 5-8 | 1 Dev + QA | Stakeholder review
Go-Live & Monitoring | 2-3 | 1 Dev | DNS, CDN, monitoring
Phase 10 Subtotal | 20-32
TOTAL ESTIMATE | 146-248 days |  | Range accounts for complexity and unknowns

## Block Priority
Block Name | Priority | Reuse | Complexity | Rationale
Header Navigation | P0 - Critical | All Pages | High | Global component, blocks all pages
Footer | P0 - Critical | All Pages | Medium | Global component, blocks all pages
Hero Section | P0 - Critical | High | Medium | 6+ variations, homepage first impression
Product Cards Grid | P0 - Critical | High | Medium | 6 variations, 40% of site pages
FAQ Accordion | P1 - High | High | Low | 4+ pages, reusable component
Offer Cards Carousel | P1 - High | Medium | Medium | Homepage, conversion pages
Anchor Navigation | P1 - High | Medium | Low | 5+ pages with sections
CTA Banner | P1 - High | Medium | Low | Multiple pages, simple variations
Case Studies Carousel | P1 - High | Medium | Medium | Community, industry pages
Email Subscription | P1 - High | All Pages | Medium | Global, form integration
Pricing Cards | P2 - Medium | Low | High | Plans page, complex tabs
Interactive Map | P2 - Medium | Low | High | Coverage page only, Leaflet integration
Industry Cards | P2 - Medium | Low | Medium | Industry solutions pages
Article Body | P2 - Medium | Medium | Low | News/blog pages
Video Feature | P2 - Medium | Low | Medium | Power, Apps pages
Impacts Table | P3 - Low | Low | High | Eligibility page only
Developer Program | P3 - Low | Low | Low | Apps page only
404 Error Content | P3 - Low | Low | Low | Single page

## Template Strategy
Template Name | Page Count | Blocks Used | Import Strategy
Device Detail | ~280 | Device Hero, Shop CTA, Legal Footnotes | Bulk import - highest volume
News Article | ~100 | Article Header, Date, Hero Image, Body Content | Bulk import from CMS
Blog Post | ~40 | Article Header, Date, Body Content | Bulk import from CMS
Industry Detail | ~8 | Industry Hero, Anchor Nav, Features, Stories, Get Started | Manual - unique content
Help Topic | ~50 | Hero with Login, Topic Grid, Accordions | Semi-automated
FAQ Category | ~30 | Help Cards, Quick Links, FAQ Accordions | Semi-automated
Offer Landing | ~25 | Offer Hero, Benefits, Device Cards, FAQ | Manual - promotional
Core Landing | ~15 | Hero, Feature Cards, CTAs, Email Subscription | Manual - high visibility
App Detail | ~50 | App Hero, Catalog Features, CTAs | Bulk import
Case Study | ~30 | Article layout with embedded media | Semi-automated
TOTAL | ~700

## Risk Assessment
Risk | Likelihood | Impact | Mitigation
Interactive Map Complexity | High | Medium | Consider iframe embed or simplified static map initially
Dynamic Content/Personalization | Medium | High | Identify personalized sections early, plan for edge functions
Form Integrations | Medium | Medium | Document current form backends, plan API integration
Authentication Flows | Low | High | Login/account pages may need custom solution
Third-party Scripts | Medium | Medium | Audit current analytics, chat, tracking scripts
SEO Redirect Complexity | Medium | High | Build comprehensive redirect map early
Content Freeze Coordination | High | Medium | Plan migration window with content team
Brand/Design Changes | Medium | Medium | Lock design tokens early, plan for updates
Device Catalog Updates | High | Low | Build flexible import scripts for ongoing updates
Performance Targets | Low | Medium | EDS typically exceeds targets, monitor LCP for carousels