## Executive Summary
AT&T Business Migration Plan - Executive Summary
Source | https://www.business.att.com/
Target Platform | Adobe Edge Delivery Services (EDS)
Authoring | Universal Editor with AEM as Content Source
Document Version | 1.2
Date | February 2026
KEY METRICS | Manual Approach | With EC/AEMCoder
Total Pages to Migrate | 749 | 749
Product Portfolios | 7 | 7
Industry Verticals | 12 | 12
Individual Products | 50+ | 50+
Custom Blocks Required | 45 | 45
Estimated Duration | 28-30 weeks | 24-26 weeks
Total Project Hours | 7,250 hours | 6,450 hours
Team Size | 12-14 FTEs | 11-13 FTEs
Estimated Cost | $1,390,000 | $1,235,000
Savings with EC/AEMCoder | - | ~$155,000 (11%)

## Migration Steps Detail
AT&T Business Migration - Detailed Steps & Hour Estimates (749 Pages)
Step # | Phase | Activity | Owner | Manual Hrs | EC Hrs | Deliverables | Why This Step Is Needed
PHASE 0: PRE-MIGRATION (Weeks 1-2)
0a | Pre-Migration | Site audit & inventory (749 pages) | Content Strategist | 40 | 40 | Complete page inventory, asset list | Understand full scope of migration; identify all pages, templates, and assets to prevent surprises later
0b | Pre-Migration | Performance baseline | Tech Lead | 24 | 24 | Current Core Web Vitals report | Establish metrics to measure improvement; prove ROI of migration to stakeholders
0c | Pre-Migration | SEO audit | SEO Specialist | 40 | 40 | Rankings, meta data, structured data | Preserve search rankings; identify critical SEO elements that must be maintained post-migration
0d | Pre-Migration | Stakeholder alignment & kickoff | PM | 24 | 24 | RACI matrix, kickoff deck, timeline | Align expectations; define roles and responsibilities; get executive buy-in for timeline and budget
0e | Pre-Migration | Technical discovery | Tech Lead | 40 | 40 | API inventory, integration mapping | Identify all backend dependencies (APIs, forms, search) that must work post-migration
|  | Phase 0 Subtotal |  | 168 | 168
PHASE 1: FOUNDATION (Weeks 3-6)
1a | Foundation | GitHub repository setup | Tech Lead | 8 | 8 | Repo with branch protection, access controls | Version control foundation; enables CI/CD, code review, and collaboration
1b | Foundation | AEM Cloud Service provisioning | DevOps | 16 | 16 | Dev, Stage, Prod environments | Required infrastructure for content authoring and Universal Editor
1c | Foundation | EDS site registration & configuration | Tech Lead | 8 | 8 | Registered site with aem.live | Enables Edge Delivery Services; connects GitHub to EDS infrastructure
1d | Foundation | fstab.yaml & site configuration | Dev Team | 8 | 8 | Content source mapping, helix config | Maps AEM content to EDS; defines site behavior and routing
1e | Foundation | CI/CD pipeline setup | DevOps | 10 | 10 | GitHub Actions for preview/publish | Automates deployment; enables continuous preview and publishing
1f | Foundation | Run EC/AEMcoder for initial migration | Dev Team | 80 | 40 | Initial blocks, markdown, page structure | Accelerate migration by auto-generating block structure and content mapping from source site
1g | Foundation | Update blocks, functionality, CSS | Dev Team | 160 | 80 | Production-ready block code | Refine auto-generated code to meet AT&T brand standards and functional requirements
1h | Foundation | Extract design system tokens | Dev Team | 80 | 60 | styles.css, CSS custom properties | Ensure visual consistency with existing brand; enable global style changes from single source
1i | Foundation | Typography & font setup | Dev Team | 24 | 24 | fonts.css, AT&T brand fonts | AT&T brand compliance requires specific fonts (Aleck Sans/Slab); legal requirement
1j | Foundation | Core navigation blocks | Dev Team | 80 | 80 | header/, footer/, mega-menu | Navigation is on every page; must work perfectly for user experience and SEO
|  | Phase 1 Subtotal |  | 474 | 334
PHASE 2: CONTENT MODELING (Weeks 7-8)
2a | Content Modeling | Create component-model.json | Tech Lead | 60 | 54 | JCR package structure for AEM importer | Required for AEM importer to create proper JCR node structure; enables content import
2b | Content Modeling | Create component-definitions.json | Tech Lead | 60 | 54 | Universal Editor field definitions | Defines authoring UI in Universal Editor; required for content authors to edit pages
2c | Content Modeling | Define content fragment models | Content Strategist | 40 | 36 | CF models for products, stories | Structure reusable content (products, testimonials) for consistency across 749 pages
2d | Content Modeling | Update transformations | Dev Team | 40 | 36 | Import script transformations | Customize how source content maps to EDS blocks; handle edge cases in content structure
|  | Phase 2 Subtotal |  | 200 | 180
PHASE 3: BLOCK DEVELOPMENT (Weeks 9-14)
3a | Block Development | Hero blocks (6 variants) | Dev Team | 120 | 72 | hero-video, hero-carousel, hero-split, etc. | Hero sections are above-the-fold; critical for first impressions and conversion rates
3b | Block Development | Card blocks (10 variants) | Dev Team | 200 | 100 | cards-product, cards-feature, cards-pricing, etc. | Cards display products/features across site; most reused block type on 749 pages
3c | Block Development | Interactive blocks | Dev Team | 280 | 168 | tabs, accordion, carousel, modal, search | Enable user engagement; required for FAQs, product details, filtering functionality
3d | Block Development | Form blocks | Dev Team | 120 | 72 | lead-form, contact-form, newsletter | Lead capture is business-critical; forms drive revenue and customer acquisition
3e | Block Development | Content blocks | Dev Team | 160 | 80 | columns, quote, table, embed, download | Support varied content layouts; enable rich content authoring flexibility
3f | Block Development | Product-specific blocks | Dev Team | 200 | 108 | pricing-table, comparison, spec-sheet | AT&T-specific functionality for product comparison and pricing display
|  | Phase 3 Subtotal |  | 1080 | 600
PHASE 4: PAGE REVIEW & ASSET MIGRATION (Weeks 15-20)
4a | Assets | Review each page, re-author assets (749 pages) | Content Team | 750 | 750 | Validated content in AEM DAM | Ensure content accuracy; fix migration errors; update outdated information
4b | Assets | Create URL redirect mapping (749 URLs) | Content Strategist | 150 | 150 | 301 redirect spreadsheet | Preserve SEO rankings; prevent broken links; maintain user bookmarks (TBD if URLs change)
4c | Assets | DAM asset migration | Content Team | 300 | 300 | Assets with metadata in AEM | Images/PDFs must be in AEM DAM for authoring; metadata enables search and governance
4d | Assets | Image optimization | Dev Team | 150 | 150 | WebP conversion, lazy loading | Performance requirement; Core Web Vitals depend on optimized images
|  | Phase 4 Subtotal |  | 1350 | 1350
PHASE 5: EDGE WORKERS & APIs (Weeks 21-22)
5a | Edge Workers | Move servlets/APIs to Edge workers | Dev Team | 160 | 160 | Edge worker functions | EDS is static; dynamic functionality (forms, search, pricing) requires edge workers
5b | Edge Workers | Pricing API integration | Dev Team | 60 | 60 | Dynamic pricing endpoints | Business requirement; pricing must be real-time and accurate for customer trust
5c | Edge Workers | Lead form submission handling | Dev Team | 40 | 40 | Form backend integration | Revenue-critical; form submissions must reach CRM/sales systems reliably
5d | Edge Workers | Search functionality | Dev Team | 80 | 80 | Site search implementation | User experience requirement; customers expect to search across 749 pages
|  | Phase 5 Subtotal |  | 340 | 340
PHASE 6: AEM MIGRATION (Weeks 23-24)
6a | AEM Migration | Migrate custom functionality to AEMaaCS | Dev Team | 120 | 120 | Reports, scheduled jobs | Preserve existing business logic; scheduled reports and jobs must continue working
6b | AEM Migration | Migrate meta-schema, taxonomy, workflows | Tech Lead | 80 | 80 | AEM configurations | Content governance requires proper taxonomy; workflows enable approval processes
6c | AEM Migration | User/group migration | Admin | 40 | 40 | Permissions in AEMaaCS | Security requirement; preserve access controls and content permissions
6d | AEM Migration | Workflow configuration | Tech Lead | 40 | 40 | Approval workflows | Business process requirement; content must go through approval before publishing
|  | Phase 6 Subtotal |  | 280 | 280
PHASE 7: INTEGRATIONS (Weeks 25-26)
7a | Integrations | Analytics/tracking setup | Dev Team | 60 | 60 | Adobe Launch configuration | Business intelligence requirement; track conversions, user behavior, ROI
7b | Integrations | Third-party scripts | Dev Team | 40 | 40 | Chat, pixels, consent banner | Customer support (chat), marketing (pixels), legal compliance (consent)
7c | Integrations | Search indexing configuration | Dev Team | 40 | 40 | Sitemap, robots.txt | SEO requirement; search engines must be able to crawl and index all 749 pages
7d | Integrations | Social meta tags | Dev Team | 20 | 20 | OG tags, Twitter cards | Social sharing requirement; proper previews when pages are shared on social media
|  | Phase 7 Subtotal |  | 160 | 160
PHASE 8: VALIDATION & TESTING (Weeks 27-28)
8a | Validation | Validate all functionalities (749 pages) | QA Team | 300 | 280 | Functional test reports | Ensure nothing is broken; verify all interactive elements work correctly
8b | Validation | Accessibility audit (WCAG 2.1 AA) | QA Team | 120 | 110 | Accessibility report, fixes | Legal requirement; ADA compliance mandatory for enterprise sites
8c | Validation | Performance/load testing | QA Team | 80 | 75 | Performance test results | Verify Core Web Vitals targets met; ensure site handles expected traffic
8d | Validation | SEO validation (749 redirects) | SEO Specialist | 80 | 80 | Redirect testing, sitemap validation | Verify no SEO ranking loss; confirm all redirects work correctly
8e | Validation | Security review | Security Team | 40 | 40 | Security headers, CSP audit | Security requirement; protect against XSS, clickjacking, data breaches
|  | Phase 8 Subtotal |  | 620 | 585
PHASE 9: LAUNCH (Weeks 29-30)
9a | Launch | Domain/DNS configuration | DevOps | 16 | 16 | Custom domain, SSL certificates | Production readiness; secure HTTPS required for customer trust and SEO
9b | Launch | UAT & stakeholder sign-off | PM | 100 | 95 | Sign-off documentation | Business approval required before go-live; stakeholders verify requirements met
9c | Launch | DNS cutover & rollback plan | Tech Lead | 40 | 40 | Production deployment | Safe deployment; rollback plan ensures quick recovery if issues arise
9d | Launch | Author training on Universal Editor | Training Lead | 80 | 80 | Training materials, sessions | Enable content team to maintain site post-launch; reduce support burden
9e | Launch | Hypercare & monitoring setup | DevOps | 100 | 100 | Monitoring dashboards, alerts | Catch issues quickly post-launch; ensure 99.9% uptime SLA is met
|  | Phase 9 Subtotal |  | 336 | 331
SUMMARY (749 PAGES)
|  | Base Hours Total |  | 5008 | 4328
|  | Contingency (~45% / ~49%) |  | 2242 | 2122 |  | Buffer for unknowns, scope changes, and discovered complexity
|  | GRAND TOTAL |  | 7250 | 6450
|  | Hours Saved with EC/AEMCoder |  |  | 800 |  | ~11% reduction in effort
|  | Weeks Saved |  |  | 4-6 weeks |  | Faster time to market

## Templates
Page Template Classification (749 Pages Total)
Template Type | Count | Complexity | Examples
Homepage | 1 | Very High | Hero carousel, product tabs, CTAs, forms
Portfolio Landing | 7 | High | Cloud, 5G, Internet, Security, IoT, Voice, Wireless
Product Detail | 150+ | Medium-High | Individual product pages with specs, pricing
Industry Landing | 12 | Medium-High | Vertical-specific solutions
Industry Solution | 80+ | Medium | Sub-pages for industry features
Article/Story | 200+ | Medium | Customer stories, blog posts
Research Report | 50+ | Medium | Downloadable content with forms
Support/Contact | 20 | Medium | Forms, contact info, FAQs
Offers/Deals | 30+ | High | Dynamic pricing, promotions
Utility | 200+ | Low | Legal, sitemap, accessibility, misc
TOTAL | 749

## Phase Summary
Migration Phases Summary (749 Pages)
Phase | Weeks | Manual Hrs | EC/AEMCoder Hrs | Savings | Key Activities
Phase 0: Pre-Migration | 1-2 | 168 | 168 | 0 | Site audit (749 pages), performance baseline, SEO audit
Phase 1: Foundation | 3-6 | 474 | 334 | 140 | Env setup, EDS config, EC/AEMcoder, blocks, design system
Phase 2: Content Modeling | 7-8 | 200 | 180 | 20 | component-model.json, component-definitions.json
Phase 3: Block Development | 9-14 | 1,080 | 600 | 480 | Hero, Card, Interactive, Form, Content, Product blocks
Phase 4: Assets (749 pages) | 15-20 | 1,350 | 1,350 | 0 | Page review, URL redirects, DAM migration
Phase 5: Edge Workers | 21-22 | 340 | 340 | 0 | Servlet/API migration, pricing API, forms, search
Phase 6: AEM Migration | 23-24 | 280 | 280 | 0 | Custom functionality, meta-schema, users, workflows
Phase 7: Integrations | 25-26 | 160 | 160 | 0 | Analytics, third-party scripts, search indexing
Phase 8: Validation (749 pages) | 27-28 | 620 | 585 | 35 | Testing, accessibility, performance, SEO
Phase 9: Launch | 29-30 | 336 | 331 | 5 | Domain/DNS, UAT, cutover, training, hypercare
Contingency | - | 2,242 | 2,122 | 120 | Risk buffer (~45%)
TOTAL | 28-30 / 24-26 | 7,250 | 6,450 | 800 | ~11% reduction

## Block Requirements
Block Requirements - 45 Total Blocks
NOTE: EC/AEMCoder Hours = Refinement work after automated block generation
NAVIGATION BLOCKS (4) - Manual development required (complex interactions)
Block Name | Complexity | Manual Hrs | EC Hrs | Why Refinement Still Needed
header | Very High | 30 | 30 | Mega-menu requires custom JS for dropdowns, hover states, mobile toggle
footer | High | 20 | 20 | Multi-region links, dynamic year, legal compliance requirements
breadcrumb | Low | 10 | 10 | Schema.org structured data, dynamic path generation
mobile-nav | High | 20 | 20 | Touch gestures, nested accordion behavior, focus management
HERO BLOCKS (6) - EC generates structure, refinement for brand/interactions
Block Name | Complexity | Manual Hrs | EC Hrs | Why Refinement Still Needed
hero-video | High | 24 | 14 | Video autoplay policies, fallback images, mobile optimization
hero-carousel | High | 24 | 14 | Swipe gestures, auto-rotation pause on hover, dot navigation
hero-tabs | High | 24 | 14 | Tab panel ARIA roles, keyboard navigation, content lazy-load
hero-split | Medium | 16 | 10 | Responsive breakpoint tuning, image aspect ratio handling
hero-minimal | Low | 16 | 10 | Typography fine-tuning, spacing adjustments per brand
hero-promo | Medium | 16 | 10 | Dynamic pricing display, countdown timer integration
CARD BLOCKS (10) - EC generates well, minor brand refinement
Block Name | Complexity | Manual Hrs | EC Hrs | Why Refinement Still Needed
cards-product | Medium | 20 | 10 | Hover states, price formatting, "Add to cart" integration
cards-feature | Medium | 20 | 10 | Icon alignment, responsive grid behavior
cards-pricing | High | 24 | 12 | Price comparison logic, "Most Popular" badge, toggle monthly/annual
cards-industry | Medium | 20 | 10 | Industry icon mapping, hover animations
cards-story | Medium | 20 | 10 | Thumbnail cropping, read time calculation, category tags
cards-stat | Medium | 20 | 10 | Number animation on scroll, suffix/prefix handling
cards-cta | Low | 16 | 8 | Button variant styling, tracking attributes
cards-icon | Medium | 20 | 10 | SVG icon color inheritance, spacing consistency
cards-testimonial | Medium | 20 | 10 | Quote styling, avatar fallbacks, company logo placement
cards-link | Low | 20 | 10 | Arrow icon animation, visited state styling
INTERACTIVE BLOCKS (10) - Require significant JS refinement
Block Name | Complexity | Manual Hrs | EC Hrs | Why Refinement Still Needed
accordion | Medium | 24 | 14 | ARIA expanded states, smooth height animation, multi-open option
tabs | Medium | 24 | 14 | Keyboard arrow navigation, ARIA tablist roles, lazy content load
carousel | High | 32 | 19 | Touch/swipe support, infinite loop, responsive slides per view
modal | Medium | 24 | 14 | Focus trap, escape key close, scroll lock on body
video | Medium | 24 | 14 | YouTube/Vimeo API integration, custom controls, tracking events
video-modal | High | 32 | 19 | Lightbox overlay, video pause on close, responsive sizing
search | High | 32 | 19 | Autocomplete, debounced API calls, result highlighting
filter | High | 32 | 19 | Multi-select logic, URL state sync, clear all functionality
pricing-calculator | Very High | 32 | 19 | Complex business logic, real-time API calls, validation
comparison-table | High | 24 | 17 | Sticky headers, horizontal scroll on mobile, highlight differences
CONTENT BLOCKS (8) - EC generates well, minimal refinement
Block Name | Complexity | Manual Hrs | EC Hrs | Why Refinement Still Needed
columns | Low | 16 | 8 | Responsive stacking order, gap consistency
quote | Low | 16 | 8 | Quotation mark styling, attribution formatting
table | Medium | 24 | 12 | Responsive horizontal scroll, sortable headers option
embed | Medium | 24 | 12 | Aspect ratio preservation, lazy loading, consent wrapper
download | Low | 16 | 8 | File type icons, size display, download tracking
cta-banner | Medium | 24 | 12 | Background image positioning, button placement variants
divider | Low | 16 | 8 | Spacing tokens, optional icon/text in divider
icon-list | Medium | 24 | 12 | Icon color theming, vertical/horizontal layout options
FORM BLOCKS (4) - Require validation and backend integration
Block Name | Complexity | Manual Hrs | EC Hrs | Why Refinement Still Needed
lead-form | High | 36 | 22 | Field validation, CRM integration, GDPR consent, error states
contact-form | Medium | 28 | 17 | reCAPTCHA integration, email formatting, success/error messages
newsletter | Medium | 28 | 17 | Email validation, double opt-in flow, Mailchimp/Marketo integration
search-input | Medium | 28 | 16 | Autocomplete dropdown, clear button, voice search option
AT&T-SPECIFIC BLOCKS (3) - Brand-specific customization
Block Name | Complexity | Manual Hrs | EC Hrs | Why Refinement Still Needed
guarantee-banner | Medium | 24 | 13 | Legal text formatting, icon animation, link to terms
offer-card | High | 32 | 17 | Dynamic offer API, expiration countdown, personalization rules
jd-power-badge | Low | 16 | 8 | Badge image optimization, award year update, tooltip
BLOCK TOTALS
Category | Count | Manual Hrs | EC Hrs | Reduction
Navigation | 4 | 80 | 80 | 0% (manual required)
Hero | 6 | 120 | 72 | 40%
Cards | 10 | 200 | 100 | 50%
Interactive | 10 | 280 | 168 | 40%
Content | 8 | 160 | 80 | 50%
Forms | 4 | 120 | 72 | 40%
AT&T-Specific | 3 | 72 | 38 | 47%
TOTAL | 45 | 1032 | 610 | ~41%

## EC Refinement Details
EC/AEMCoder Block Refinement - Why Hours Are Still Needed
EC/AEMCoder generates initial block structure, CSS scaffolding, and content mapping.
The hours below represent REFINEMENT work required after automated generation.
REFINEMENT CATEGORY | Description | Typical Effort | Blocks Affected
1. BRAND COMPLIANCE
AT&T color tokens | Map generated colors to AT&T brand palette (#009FDB, #0568AE) | 2-4 hrs/block | All blocks
Typography tuning | Apply AT&T Aleck Sans/Slab fonts, adjust line heights | 1-2 hrs/block | All blocks
Spacing consistency | Align padding/margins to AT&T design system grid | 1-2 hrs/block | All blocks
2. ACCESSIBILITY (WCAG 2.1 AA)
ARIA attributes | Add aria-label, aria-expanded, aria-controls, roles | 2-4 hrs/block | Interactive, Forms
Keyboard navigation | Tab order, Enter/Space activation, arrow key support | 2-4 hrs/block | Interactive, Nav
Focus management | Visible focus rings, focus trap in modals | 1-2 hrs/block | Modal, Forms
Screen reader testing | VoiceOver/NVDA testing and fixes | 2-3 hrs/block | All blocks
3. RESPONSIVE BEHAVIOR
Mobile breakpoints | Adjust layouts for 320px-768px viewports | 2-4 hrs/block | All blocks
Touch interactions | Swipe gestures, tap targets (44px min) | 2-3 hrs/block | Carousel, Nav
Image optimization | srcset, lazy loading, aspect ratio handling | 1-2 hrs/block | Hero, Cards
4. COMPLEX INTERACTIONS (Not automated)
State management | Open/close states, active tabs, selected filters | 4-8 hrs/block | Interactive
Animation/transitions | Smooth height changes, fade effects, slide animations | 2-4 hrs/block | Accordion, Modal
API integration | Fetch data, handle loading/error states | 4-8 hrs/block | Search, Pricing
Form validation | Field validation, error messages, submit handling | 4-6 hrs/block | Forms
5. TESTING & QA
Cross-browser testing | Chrome, Safari, Firefox, Edge verification | 1-2 hrs/block | All blocks
Device testing | iOS Safari, Android Chrome, tablet layouts | 1-2 hrs/block | All blocks
Edge case handling | Empty states, long text, missing images | 1-2 hrs/block | Cards, Content

## Resources
Team Structure & Hours by Phase (749 Pages)
Role | Count | Rate/Hr | Ph 0 | Ph 1 | Ph 2 | Ph 3 | Ph 4-6 | Ph 7-9 | Total Hrs | Total Cost
Project Manager | 1 | $150 | 30 | 40 | 20 | 60 | 100 | 120 | 370 | $55,500
Technical Lead | 1 | $200 | 80 | 100 | 100 | 120 | 160 | 100 | 660 | $132,000
Sr. EDS Developer 1 | 1 | $185 | 0 | 130 | 40 | 320 | 280 | 100 | 870 | $160,950
Sr. EDS Developer 2 | 1 | $185 | 0 | 110 | 40 | 280 | 280 | 100 | 810 | $149,850
Mid EDS Developer 1 | 1 | $165 | 0 | 90 | 0 | 200 | 220 | 100 | 610 | $100,650
Mid EDS Developer 2 | 1 | $165 | 0 | 50 | 0 | 160 | 180 | 80 | 470 | $77,550
Jr. EDS Developer | 1 | $140 | 0 | 30 | 0 | 80 | 120 | 80 | 310 | $43,400
Content Strategist | 1 | $135 | 60 | 20 | 80 | 40 | 150 | 60 | 410 | $55,350
Content Author 1 | 1 | $95 | 0 | 0 | 0 | 0 | 400 | 80 | 480 | $45,600
Content Author 2 | 1 | $95 | 0 | 0 | 0 | 0 | 350 | 60 | 410 | $38,950
Content Author 3 | 1 | $95 | 0 | 0 | 0 | 0 | 300 | 40 | 340 | $32,300
QA Engineer | 1 | $130 | 0 | 0 | 0 | 0 | 160 | 400 | 560 | $72,800
SEO Specialist | 0.5 | $140 | 40 | 0 | 0 | 0 | 0 | 80 | 120 | $16,800
DevOps/Admin | 0.5 | $160 | 0 | 34 | 0 | 0 | 80 | 116 | 230 | $36,800
TOTAL | 12-14 |  | 210 | 604 | 280 | 1260 | 2780 | 1516 | 6650 | $1,018,500

## Cost Summary
Cost Estimation Summary (749 Pages)
LABOR COSTS BY PHASE
Phase | Hours | Labor Cost | % of Total
Phase 0: Pre-Migration | 168 | $28,000 | 2%
Phase 1: Foundation (incl. env setup) | 474 | $80,000 | 7%
Phase 2: Content Modeling | 200 | $36,000 | 3%
Phase 3: Block Development | 1080 | $187,000 | 16%
Phase 4-6: Migration (749 pages) | 1970 | $315,000 | 27%
Phase 7-9: Validation/Launch | 1116 | $180,000 | 15%
Contingency | 2242 | $364,000 | 30%
TOTAL | 7250 | $1,190,000 | 100%
ADDITIONAL COSTS
Item | Monthly | Annual | Notes
Adobe EDS Licensing | TBD | TBD | Per Adobe agreement
AEM Cloud Service | TBD | TBD | Per Adobe agreement
Search Service (Algolia) | $1,500 | $18,000 | Enterprise search (749 pages)
Edge Worker Compute | $800 | $9,600 | Cloudflare/similar (higher traffic)
Image CDN | $500 | $6,000 | Image optimization
Monitoring Tools | $500 | $6,000 | Datadog/New Relic
Subtotal Additional |  | $39,600 | First year
TOTAL PROJECT COST SUMMARY
Category |  | Manual | EC/AEMCoder
Labor |  | $1,190,000 | $1,030,000
Additional Costs (Year 1) |  | $39,600 | $39,600
Contingency (~15%) |  | $160,400 | $145,000
PROJECT TOTAL |  | $1,390,000 | $1,215,000
SAVINGS |  |  | ~$175,000 (13%)

## Risk Assessment
Risk Assessment (749 Pages)
Risk | Probability | Impact | Mitigation
Complex mega-menu navigation | High | High | Technical spike early, fallback options
Pricing API integration | Medium | High | Early API documentation, mock services
Content approval delays (749 pages) | High | Very High | Phased reviews, 3 dedicated content authors
AT&T brand compliance | Medium | High | Early brand team engagement
Edge worker complexity | Medium | High | Prototype critical workers first
Third-party script conflicts | Medium | Medium | Staged integration, testing
SEO ranking impact (749 redirects) | Medium | High | Comprehensive redirect strategy, monitoring
Performance with dynamic content | Medium | Medium | Caching strategy, edge optimization
Content volume overwhelming team | High | High | Add 3rd content author, batch processing
QA coverage for 749 pages | Medium | High | Automated testing, sampling strategy
AEM Cloud Service provisioning delays | Medium | High | Request environments early in Phase 1

## Manual vs EC-AEMCoder
EC/AEMCoder vs Manual Approach Comparison (749 Pages)
OVERALL COMPARISON
Metric | Manual | EC/AEMCoder | Savings
Duration | 28-30 weeks | 24-26 weeks | 4-6 weeks
Total Hours | 7,250 | 6,450 | 800 hours
Total Cost | $1,390,000 | $1,215,000 | $175,000
Percentage Reduction | - | - | ~13%
Team Size | 12-14 FTEs | 11-13 FTEs | 1-2 FTEs

## Success Criteria
Success Criteria (749 Pages)
TECHNICAL SUCCESS METRICS
Metric | Target
Lighthouse Performance | > 90
Lighthouse Accessibility | > 95
Lighthouse SEO | > 95
Core Web Vitals (all) | Pass
Cross-browser compatibility | Chrome, Safari, Firefox, Edge
Mobile responsiveness | 100% of 749 pages
Page load time (LCP) | < 2.5s
BUSINESS SUCCESS METRICS
Metric | Target
Page load time improvement | > 40%
Content authoring time | < 50% of current
Time to publish | < 5 minutes
Uptime SLA | 99.9%
Lead form conversion | Maintain or improve
SEO rankings | No degradation across 749 pages
Redirect success rate | > 99.5% (749 URLs)